Minutes

of the

Saint-Petersburg, May 23 -25, 2016

Methodology of OS and QF development. (Part1).

European Dimension in Qualifications for the Tourist Sector/EurDiQ/

Participants:

- Yianna Orphanidou – UNic

- Melpo Iacovidou– UNic

- Elena Gorbashko – SPbSUE

- Elena Vasileva – SPbSUE

- Galina Karpova– SPbSUE

- Nataly Smith - RSUTS

- Irina Maevskay - DSTU

- Shvedova Svetlana - DSTU

- Olga Subanova - FU

- Elvira Sagyntay - IKSU

- lona Ansone –Baltic RUTI, EU Key expert of enterprises

- Ludmila Ivanova - Baltic RUTI, RU Key expert of enterprises

- Marina Gunare – BIA

- Prof. Gerald Wetzel FHM

- Pia Winkler – FHM

- Sergey Romanov– SSU

- Ludmila Belosludseva - SSU

- Yriy Schegolkov –FU

- Tatiana Rosanova –FU

- Lilia Prihodko-FU

- Abdyldaev Kurmanbek Kyianovich- IKSU

- Rahat Kermaliev - IKSU

- Larisa Marchenko – MESK

- Renata Eras - Independent Expert for Quality

1. Meeting program:

23.05.2016 Presentation of research from the partners institutions

FU – “Tendencies of Tourist Market Development in Russia”

RSUTS – “Analysis of Russian experience in OS and QF development for Russian tourist sector”.

SSTU – “Analysis of educational standards and educational programmers (including Bachelor and Master level) for Russian tourist sector”.

Discussions of the research results.

24.05.2016 Management team meeting.

Presentation of project accouter Zanna Chernoshtan.

Presentation of draft the Partnership Agreement(PA). Discussion of the PA Discussion of the project activities for the 2016 year, Sochi and London meetings.

Meeting with enterprises from tourist sector.

Presentation of director Baltic RUTI Ilona Ansone - “The Latvian experience in quality management in tourist sector”

Presentation of director of tourist company “Saint-Petersburg Express Service” (member of Baltic RUTI) Ludmila Ivanova – “The  needs of the specialists for Saint-Petersburg business tourist market in”

25.05.2016 Inter-project cooperation “Tempus and Erasmus +”

Presentation of the Tempus project experience in design of the Master and Bachelor programmer (Austrian experts)

2. The following meetings were planned:

 Methodological seminar (Part 2) will take place in Sochi SSU, September 15-18 , 2016. Deadline for List of the participants is 05.07.2016.

- Workshop for the Universities will take place in London, November 2016. Deadline for List of the participants in June, 2016.

3. Implementation of the project:

Signature Partnership agreement in June (all partners of the project consortium).

Topic for research. Methodological seminar (Part 2)

 SPbSUE shall draft Questionnaire for the implementation of WP 1 and distribute it among Consortium members by 15.09.16 before Workshop in Sochi.

 SPbSUE and LMU shall implement research into OS and SQF methodology by 20.11.2016 and present final ideology of OS and SQF development by SPbSUE and LMU.

Topic for discussion of management team:

Discussion of the project activities for the 2017 year, Kirgizstan and Cyprus meetings.

Discussion dates:

Research team visit to Kirgizstan – January 2017

Seminar for development Master degree program in Cyprus– May  2017

Work shop for teachers and enterprises – September 2017

4. Financial reporting:

 Each consortium member can submit Convention for the staff costs and Timesheets twice per year: by 10 of December 2016 and by 15 of May 2017 .

 In order to receive staff costs either to the institution account or private account exact Bank details should be submitted to the BIA.

 Staff costs for the arrangement of study visits to the EU partners should be requested at least two months prior the event.

 All travel tickets will be purchased by BIA.  Cost of stay will be transferred to the requested account or handed out upon arrival to the certain place of mobility.  Boarding passes and transfer receipts originals should be submitted to the BIA.  IGR should by filled in for each mobility.